## Slide 1: Tetris Weekly Presentation
By Team D

## Slide 2: Project Progress
Project Burndown: 29 of 38 requirements met
Brooks
  8 of 9 requirements met
Quay
  6 of 7 requirements met
Seth
  10 of 11 requirements met
Jacob
  5 of 11 requirements met

## Slide 3: Summary
Seth progressed with the unit testing of his three features, while Quay completed all three features and six requirements but faced delays in unit testing due to OS issues. Quay expects to finish all unit tests by November 29th. Brooks is continuing work on unit tests.

## Slide 4: Lines of Code
Quay
  80 Lines of Code
Jacob
  177 Lines of Code
Brooks
  264 Lines of Code
Seth
  158 Lines of Code

## Slide 5: Milestone 6
November 20th - November 26th, 2023
  Goal: Continue with unit testing, integration testing.

## Slide 6: Upcoming Milestone
Milestone 7 Date: November 27th - December 3rd, 2023 Goal: Complete all tests, presentation, and merge the project.